## Burndown Chart Template
Burndown Chart Template
Sprint 1 |  | Story Points
Drawing UML diagrams |  | 2
databased design and creation |  | 2
Home Page |  | 2
| Total | 6 | Velocity Sprint 1 | 6
Sprint 2
checkout page |  | 2
Cart page |  | 3
Product view |  | 3 | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
Menu |  | 4 | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
| Total | 12 | Velocity Sprint 2 | 5
Sprint 3
Product view |  | 3
Menu |  | 4
Test doument |  | 2
customization |  | 3
checkout page |  | 2
| Total | 7 | Velocity Sprint 2 | 14
Total Story Points |  | 25 | Average Velocity | 8.3333 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 25
2 | 19
3 | 14
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 25 | 6
2 | 19 | 5
3 | 14 | 14
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 25 | 6
2 | 19 | 5
3 | 14 | 14